# Study Timeline and Budget - Allergy Epidemiology Study

Study Title: Epidemiological Study on Allergy in SIMS&RH Tumkur, Karnataka

Total Duration: 16 months

Total Budget: ₹25,00,000 (approximately $30,000 USD)

## 1. Detailed Study Timeline

### Phase 1: Protocol Development and Ethical Approval (Months 1-3)

#### Month 1: Protocol Development

- Week 1-2: Literature review and protocol drafting

- Week 3-4: Questionnaire development and pilot testing

- Deliverables: Draft protocol, questionnaires, data collection forms

#### Month 2: Ethical and Administrative Preparations

- Week 1-2: Ethics committee submission preparation

- Week 3-4: Regulatory approvals and permissions

- Deliverables: Ethics submission, regulatory approvals

#### Month 3: Training and Pilot Study

- Week 1-2: Staff recruitment and training

- Week 3-4: Pilot study in small sample

- Deliverables: Trained staff, pilot study report

Milestones: Ethics approval, final protocol, trained team

### Phase 2: Main Data Collection (Months 4-10)

#### Month 4: Final Preparations

- Equipment procurement and calibration

- Final training and standardization

- Community sensitization

#### Months 5-10: Field Data Collection (6 months)

- Urban areas: Months 5-7

- Rural areas: Months 7-9

- Hospital-based recruitment: Ongoing throughout

- Laboratory sample collection: Parallel to clinical data

Weekly targets: 20-25 participants per week Quality monitoring: Weekly supervision visits

Milestones: Complete recruitment, data collection closure

### Phase 3: Laboratory Analysis (Months 8-10)

- Microbiome analysis: Months 8-9

- Microplastic analysis: Months 9-10

- Allergen testing: Ongoing

### Phase 4: Data Analysis and Report Writing (Months 11-14)

#### Month 11: Data Management

- Data entry and cleaning

- Database finalization

#### Months 12-13: Analysis

- Descriptive analysis

- Bivariate and multivariate analysis

- Microbiome and spatial analysis

#### Month 14: Report Writing

- Draft reports and manuscripts

- Results validation

### Phase 5: Dissemination (Months 15-16)

- Publications and presentations

- Policy recommendations

- Community feedback

## 2. Gantt Chart Summary

Months: 1  2  3  4  5  6  7  8  9 10 11 12 13 14 15 16
Protocol Development     ████
Ethical Approval         ████
Training                 ████
Data Collection                ████████
Lab Analysis                    ████
Data Analysis                        ████
Report Writing                          ████
Dissemination                              ██

## 3. Detailed Budget Breakdown

### 3.1 Personnel Costs (₹12,00,000 - 48%)

| Position | Number | Duration | Monthly Salary | Total Cost |
| --- | --- | --- | --- | --- |
| Principal Investigator | 1 | 16 months | ₹50,000 | ₹8,00,000 |
| Co-Investigator | 2 | 12 months | ₹40,000 | ₹9,60,000 |
| Research Coordinator | 1 | 16 months | ₹25,000 | ₹4,00,000 |
| Data Manager | 1 | 12 months | ₹20,000 | ₹2,40,000 |
| Field Investigators | 6 | 7 months | ₹15,000 | ₹6,30,000 |
| Laboratory Technician | 2 | 6 months | ₹18,000 | ₹2,16,000 |
| Data Entry Operators | 3 | 8 months | ₹12,000 | ₹2,88,000 |
| Statistical Consultant | 1 | 4 months | ₹40,000 | ₹1,60,000 |
| Microbiome Specialist | 1 | 3 months | ₹50,000 | ₹1,50,000 |
| GIS Specialist | 1 | 3 months | ₹35,000 | ₹1,05,000 |
| Subtotal Personnel |  |  |  | ₹39,49,000 |

*Note: Salaries include HRA and conveyance allowances

### 3.2 Equipment and Supplies (₹4,50,000 - 18%)

| Item | Quantity | Unit Cost | Total Cost |
| --- | --- | --- | --- |
| Skin prick test kits | 1,200 | ₹500 | ₹6,00,000 |
| Peak flow meters | 6 | ₹2,000 | ₹12,000 |
| Anthropometric equipment | 6 sets | ₹5,000 | ₹30,000 |
| GPS devices | 6 | ₹8,000 | ₹48,000 |
| Laboratory consumables | - | - | ₹1,50,000 |
| Microbiome analysis kits | 200 | ₹5,000 | ₹10,00,000 |
| Microplastic analysis | 200 | ₹3,000 | ₹6,00,000 |
| Data collection tablets | 6 | ₹15,000 | ₹90,000 |
| Office supplies | - | - | ₹50,000 |
| Subtotal Equipment |  |  | ₹24,80,000 |

### 3.3 Travel and Transportation (₹2,50,000 - 10%)

| Activity | Details | Estimated Cost |
| --- | --- | --- |
| Field visits | 6 investigators × 7 months × ₹5,000 | ₹2,10,000 |
| Sample transportation | Cold chain for biological samples | ₹40,000 |
| Training workshops | Travel for training sessions | ₹30,000 |
| Monitoring visits | Supervisor travel | ₹50,000 |
| Subtotal Travel |  | ₹3,30,000 |

### 3.4 Laboratory Analysis (₹3,00,000 - 12%)

| Analysis Type | Details | Cost |
| --- | --- | --- |
| Skin prick testing | 1,200 tests | ₹1,00,000 |
| Microbiome sequencing | 200 samples × ₹8,000 | ₹16,00,000 |
| Microplastic analysis | 200 samples × ₹5,000 | ₹10,00,000 |
| Quality control | External validation | ₹50,000 |
| Subtotal Laboratory |  | ₹27,50,000 |

### 3.5 Data Management and Analysis (₹1,50,000 - 6%)

| Item | Details | Cost |
| --- | --- | --- |
| Software licenses | REDCap, statistical software | ₹50,000 |
| Data storage | Secure cloud storage | ₹30,000 |
| Computer hardware | Additional computers/tablets | ₹50,000 |
| Internet connectivity | Field data transmission | ₹20,000 |
| Subtotal Data Management |  | ₹1,50,000 |

### 3.6 Training and Capacity Building (₹50,000 - 2%)

| Activity | Details | Cost |
| --- | --- | --- |
| Staff training | Workshops and certification | ₹30,000 |
| Community sensitization | Awareness programs | ₹20,000 |
| Subtotal Training |  | ₹50,000 |

### 3.7 Publication and Dissemination (₹1,00,000 - 4%)

| Activity | Details | Cost |
| --- | --- | --- |
| Publication fees | Open access journals | ₹50,000 |
| Conference registration | National/international | ₹30,000 |
| Printing materials | Reports and brochures | ₹20,000 |
| Subtotal Dissemination |  | ₹1,00,000 |

### 3.8 Contingency (₹2,00,000 - 8%)

- Unforeseen expenses: ₹2,00,000 (8% of total budget)

## 4. Budget Summary

| Category | Amount (₹) | Percentage |
| --- | --- | --- |
| Personnel | 12,00,000 | 48% |
| Equipment & Supplies | 4,50,000 | 18% |
| Travel & Transportation | 2,50,000 | 10% |
| Laboratory Analysis | 3,00,000 | 12% |
| Data Management | 1,50,000 | 6% |
| Training | 50,000 | 2% |
| Publication | 1,00,000 | 4% |
| Contingency | 2,00,000 | 8% |
| Total | 25,00,000 | 100% |

## 5. Funding Sources

### Primary Funding:

- Institutional funds: ₹15,00,000 (60%)

- Research grants: ₹10,00,000 (40%)

### Funding Agency Requirements:

- Quarterly progress reports

- Financial audits

- Intellectual property rights

- Publication acknowledgments

## 6. Budget Monitoring and Control

### Financial Management:

- Monthly budget tracking

- Variance analysis

- Quarterly financial reports

- Audit trail maintenance

### Cost Control Measures:

- Competitive bidding for equipment

- Bulk purchasing for consumables

- Resource sharing with other departments

- Regular budget reviews

### Risk Management:

- Budget contingency planning

- Alternative sourcing strategies

- Cost escalation monitoring

- Funding shortfall mitigation

## 7. Resource Allocation Timeline

### Year 1 (Months 1-8):

- Personnel: ₹8,00,000

- Equipment: ₹3,00,000

- Training: ₹30,000

- Initial lab analysis: ₹1,00,000

- Subtotal: ₹12,30,000

### Year 2 (Months 9-16):

- Personnel: ₹4,00,000

- Equipment: ₹1,50,000

- Lab analysis: ₹2,00,000

- Data analysis: ₹1,00,000

- Dissemination: ₹1,00,000

- Contingency: ₹2,00,000

- Subtotal: ₹11,50,000

## 8. Value for Money Considerations

### Cost-Effectiveness:

- Competitive personnel costs

- Local procurement where possible

- Shared resources utilization

- Long-term institutional benefits

### Sustainability:

- Capacity building for institution

- Reusable equipment procurement

- Knowledge transfer to local staff

- Potential for future research collaborations

## 9. Budget Approval and Monitoring

### Approval Process:

- Department review

- Institutional approval

- Funding agency approval

- Ethics committee review

### Monitoring Mechanisms:

- Monthly expenditure reports

- Quarterly budget reviews

- Annual financial audit

- Final project audit

Budget Version: 1.0 Prepared by: __________ Approved by: __________ Date: __________